## Table of Contents
Project: | Insert project name here.
To use this tool, proceed through each work tab filling out the green boxes to create the plan, and then fill in the grey boxes as you monitor and execute the plan. Underlined blue text indicates links to other work tabs. Small, red triangles in the upper right corner of a text box indicate additional comments that explain the intended content. The process is somewhat linear but will require iterative steps to complete the process. All of the tabs should be somewhat ever-green during the life of the project. Guidelines and suggestions are available on each work sheet. They provide only basic directions. If you still have questions, contact your local PMFE/TPLFE representative or the corporate PMFE leader. The guidelines can be hidden by the "-" button in the left column. Once hidden the "+" button will show them again.
Process Flow
Phase | Step | Step Name | Template | Description / PM Role
Plan | 1 | Define Scope | Deliverables list | WHAT? Determine what the project needs to accomplish and how it can be measured.
Plan | 2 | Justify Project | Business Case | WHY? Prove that this project is worth doing.
Plan | 3 | Identify Stakeholders | Stakeholder list | WHO? Determine who's affected by or needs to be involved in the project.
Plan | 4 | Develop Schedule and Resource Plan | Extended RACI | HOW? Develop list of activities and resources needed to complete the project.
Plan | 5 | Identify Risk Mitigation Plans | 9-box and mitigation plans | RISKS? Consider what could go wrong during the program and do something about it.
Plan | 6 | Obtain Plan Approval and Commitment | Stakeholder List | APPROVE? Make sure stakeholders are "on-board" with the project plan.
Implement | 7 | Manage Stakeholders and Project Team | Stakeholder List | COMMUNICATE! Lead team & drive communication between all stakeholders during project.
Implement | 8 | Monitor Task Completion | Extended RACI (also see Deliverables List & Project Costs) | FIND ISSUES! Check that work is done on time, on quality and under cost.
Implement | 9 | Drive Resolution of Issues | Issue-Action Item List | FIX ISSUES! Lead team to recover from changes and unexpected problems.
Close Out | 10 | Close Project | Close Out Check List | FINISH! Close out meeting with stake holders
Plan | A1 | Estimate Project Costs | Project Costs | Appendix 1: Optional worksheet to estimate costs associated with completing the project
Process is semi-linear but some iteration between steps will be required.

## Deliverables List
Project Name Will Be Copied from TOC Worksheet
Deliverables List
This work tab should include the objectives of the project a.k.a. its deliverables. That is, it should define the objective of the project. INSTRUCTIONS: STEP 1 - Work with your customers to identify the deliverable description -- the objectives that the project is intended to complete. STEP 2 - For each deliverable define the tangible evidence. Evidence must meet the "SMART" criteria (see definition in SMART in the comment field below). If you struggle finding good SMART metrics you may need to break the deliverables down into more detail. STEP 3 - During the project, the R-Y-G-C column should be updated to show the status and expected achievability of each deliverable. Any significant constraints or limitations should also be listed. These may include timing targets, cost, resource constraints, etc. These limitations are critical inputs to the planning activity.
Ref. # | Description | SMART Metrics | R-Y-G-C | Comment
1
2
3
4
5
6
7
8
9
10
11
12
|  | SMART | Red / Yellow / Green / Complete
|  | S = Specific | R = off plan no recovery plan yet
|  | M = Measureable | Y = off plan with path to recovery
|  | A = Actionable | G = on plan
|  | R = Realistic | C = Complete
T = Time Constrained
Note on C10: S = Specific (… enough to be understood) M = Measureable (is this quantifiable?) A = Actionable (do I know how to do this?) R = Realistic (can I feasibly do this?) T = Time Constrained (by when does it need to be done?)
Note on D10: R = off plan no recovery plan yet Y = off plan with path to recovery G = on plan C = Complete
TOC

## Business Case
Project Name Will Be Copied from TOC Worksheet
Business Case
This work tab should be used to explain why your project is being run. Use quantified data as much as possible. A formal business case may be worked out or the project may just be required to support a larger program INSTRUCTIONS: STEP 1 - Work with your customers to identify and quantify the benefits for the project. STEP 2 - Work with your team and management, if needed, to identify and quantify the costs to complete the project. You will iterate on this step after doing more detailed resource planning in the RACI tool. STEP 3 - Compare - do the benefits exceed the costs. If there are questions then go back to your stakeholders to better understand or clarify the project.
What is the benefit this project will provide? Use quantifiable value statements where possible.
What are the costs needed complete the project?
Do the benefits justify the costs?
Note on A6: Think about why project is needed and what it will deliver and who are the customers. Use data based deliverables if possible
Note on A10: Include costs where possible. If not available describe the number of people needed, how much work is expected and any significant resources or consumed material.
Note on A14: Compare how the benefits of this project compare with the costs.
TOC

## Stakeholder List
Project Name Will Be Copied from TOC Worksheet
Stakeholder List
This work tab lists the people affected by the project and any significant resources needed. INSTRUCTIONS: STEP 1 - Identify your stakeholders --anyone who might have a significant impact on the success of your project. See the comments (red triangles) in each section below for more descriptions of the types of stakeholders. Be sure you identify each stakeholder both by organization/function and by name. STEP 2 - Think about how you will communicate with each stakeholder (e.g. email, meetings, etc.) and capture it in the "Communication Plan" column. STEP 3 - After you complete the Planning Stage steps (see the Table of Contents) then use the "Approvals" columns to document stakeholder agreement with the plan. STEP 4 - After you finish the program then use the "Approvals" column to document stakeholder agreement that the project deliverables have been met.
Key
Customer / Management Group |  |  | Approvals |  | Communication Plan Types
Organization / Function / Role | Name | Communication Plan | Plan approved? | Close Out? | Project Team Meeting | regular or semi-regular meeting for project team
[5 empty] | One-on-one update | One-on-one update of this person with project manager
[5 empty] | Customer/Management Group Update | meeting with whoever defined/requested the work to be done and the people that committed to providing resources needed
[5 empty] | Email | Regular or semi-regular email sent to some collection of stakeholders
Project Role
[5 empty] | Project Manager | who is running project
[5 empty] | Sponsor - Management Team | point of contact for project customer
[5 empty] | Customer - Management Team | managers accountable for successful completion of project
Team Members |  |  | Approvals |  | Resource Owner - Management Team | managers with oversight of resources needed for project
Organization / Function / Role | Name | Communication Plan | Plan approved? | Close Out? | Project Team Member | who is actively engaged in running project work. All tasks should be accountable to a team member.
[5 empty] | Extended Team Member | resources responsible to complete subsets of project work.
[5 empty] | Supplier | external resources needed to complete project
Other
Other Stakeholders & Significant Physical Resources |  |  | Approvals
Organization / Function / Role | Name | Communication Plan | Available?
Note on A6: The customer and management group represents who is requesting the project and who is providing the resources needed to do so. The customer may be part of the management group for internal projects and subprojects under larger programs. The customer should be consulted to define the project deliverables when the project is started. He or she should be consulted near the end to confirm that they were met before the project is closed down. The management group controls the resources needed to complete the project. They likely have a vested interest in meeting the customers needs but only be owners of resources. In general, your customers and management team will be defined at the beginning of the project during the planning stage. If additional resources are needed, you may need to add additional management group members.
Note on A7: What organization does this person fall into and what is his/her title?
Note on C7: How do you intend to communicate with each person. Suggested Communication Plan Options: - Project Team Meetings - One-on-one Updates - Customer / Management Group Updates - Email
Note on D7: Did this person confirmed that the project plan is OK, and they are available to support as indicated in the plan?
Note on E7: Did this person confirm that the project did what it was supposed to do and should be closed?
Note on A17: A project, by definition, will require a cross functional team. The team member should be listed in this area. These are the people that will be involved in a large portion of the work required to complete the project. During the early planning stage, you may or may not have defined the entire team. You may need to add more people to the team list during the program.
Note on A18: What organization does this person fall into and what is his/her title?
Note on C18: How do you intend to communicate with each person. Suggested Communication Plan Options: - Project Team Meetings - One-on-one Updates - Customer / Management Group Updates - Email
Note on D18: Did this person confirmed that the project plan is OK, and they are available to support as indicated in the plan?
Note on E18: Did this person confirm that the project did what it was supposed to do and should be closed?
Note on A29: Other stakeholders should include either people needed to complete one or two tasks but that are not needed to be engaged in the larger project. This list should also include any significant physical resources, e.g. test cells, needed for the project. This list should be developed during the planning stage as the RACI is created. If additional unplanned resources are required during the project they should be added here.
Note on A30: What organization does this person fall into and what is his/her title?
Note on C30: How do you intend to communicate with each person. Suggested Communication Plan Options: - Project Team Meetings - One-on-one Updates - Customer / Management Group Updates - Email
Note on D30: Did you confirm that this resource is available to support the plan when needed in the RACI, including confirmation from their manager, as appropriate?
TOC

## Extended RACI
Project Name Will Be Copied from TOC Worksheet
Extended RACI
INSTRUCTIONS: 'STEP 1 - List out all the tasks needed to complete the deliverables under the column "Task or Milestone Definition". STEP 2 - Put all team members names in the "Resources" columns. Additional key resources such as test cells or vehicles can be added. STEP 3 - Identify who on the team is going to be accountable for each task by putting an "A" in the box under their name (see example below). Any team members that are helping do the work should have an "R" in the box under their name. Some team members may just be consulted or informed on some tasks and should be marked with a C or I. Each task should have one person identified as accountable but may have multiple people defined as responsible, consulted or informed. STEP 4 - Work with the Accountable team member to determine the duration and timing of each task. This should be shown by filling in the boxes under the appropriate timing (see blue box example below). You should consider which tasks require other tasks to be completed before they are started. Some tasks may also have necessary lead times after they are requested. These types of relationships can be included in the comments column. STEP 5: During the project, the R-Y-G-C (RED / YELLOW / GREEN / COMPLETE) column should be updated to show the status and expected achievability of each deliverable. The comments column can be used to document status. | [40 empty] | - To add additional task rows, week columns and/or resource columns you can insert rows and columns as needed. - Use the format painter to duplicate formatting by row or by column. - If you add a week column, you'll need to update the date field in row 9.
Resources
[35 empty] | Sponsor | Project Manager | Team Member | Team Member | Physical Resource | Physical Resource
| Schedule | [6 empty] | Start Date: | 2011-02-01
Task | 2011-02-01 | 2011-02-08 | 2011-02-15 | 2011-02-22 | 2011-03-01 | 2011-03-08 | 2011-03-15 | 2011-03-22 | 2011-03-29 | 2011-04-05 | 2011-04-12 | 2011-04-19 | 2011-04-26 | 2011-05-03 | 2011-05-10 | 2011-05-17 | 2011-05-24 | 2011-05-31 | 2011-06-07 | 2011-06-14 | 2011-06-21 | 2011-06-28 | 2011-07-05 | 2011-07-12 | 2011-07-19 | 2011-07-26 | 2011-08-02 | 2011-08-09 | 2011-08-16 | 2011-08-23 | 2011-08-30 | 2011-09-06 | 2011-09-13 | Task or Milestone Definition | [6 empty] | R-Y-G-C | Comment
1 | [33 empty] | Task 1 | C |  | A
2 | [33 empty] | Task 2 |  | I |  | A | I
3 | [33 empty] | Task 3 |  |  | A | R
4 | [33 empty] | Task 4 | C | A |  | C
5 | [33 empty] | Task 5 |  |  | A |  | R
6 | [33 empty] | Task 6 | C | A | R |  |  | R
7 | [33 empty] | Task 7
8 | [33 empty] | Task 8
9 | [33 empty] | Task 9
10 | [33 empty] | Task 10
11 | [33 empty] | Task 11
12 | [33 empty] | Task 12
13 | [33 empty] | Task 13
14 | [33 empty] | Task 14
15 | [33 empty] | Task 15
16 | [33 empty] | Task 16
17 | [33 empty] | Task 17
18 | [33 empty] | Task 18
19 | [33 empty] | Task 19
20 | [33 empty] | Task 20
21 | [33 empty] | Task 21
22 | [33 empty] | Task 22
23 | [33 empty] | Task 23
24 | [33 empty] | Task 24
25 | [33 empty] | Task 25
26 | [33 empty] | Task 26
27 | [33 empty] | Task 27
28 | [33 empty] | Task 28
29 | [33 empty] | Task 29
30 | [33 empty] | Task 30
Note on AP18: R = off plan no recovery plan yet Y = off plan with path to recovery G = on plan C = Complete
R = Responsible (Does the work)
A = Accountable (Makes sure the work gets done)
C = Must be Consulted (2 way flow of information)
I = Must be Informed (1 way flow of information)
TOC

## 9-Box and Mitigation Plans
Project Name Will Be Copied from TOC Worksheet
9-Box and Mitigation Plans
This work tab should be used to outline what might go wrong in the project and get in the way of completing it, that is the risks. Each risk should be considered for how likely it is to happen and how severe the impact would be if it did. Any risks in the red or yellow boxes should be copied to the mitigation plan table in columns G through I. The team should consider mitigation plans to reduce the severity and or likelihood of the risk and add these plans to the RACI work tab by added needed tasks.
INSTRUCTIONS:
STEP 1 - Brainstorm project risks or things that may happen outside of the plan.
STEP 2 - Rate the criticality for each risk- If this risk happens how significant is it to the success of the project?
STEP 3 - Rate the likelihood for each risk-- How likely is it that this risk will happen?
STEP 4 - Document each risk on the 9-box based on their criticality and likelihood.
STEP 5 - Develop mitigation plans for the risks in the red and yellow boxes and document it in the Mitigation Plan chart.
STEP 6 - Incorporate mitigation plans in project schedule in the RACI.
|  |  | Likelihood |  | Mitigation Plan for red and yellow risks
|  | HIGH | Moderate | Low | Risk | Mitigation Plan | In RACI?
Criticality
Low
HIGH
Moderate
TOC

## Issue-Action Item List
Project Name Will Be Copied from TOC Worksheet
Issues-Action Item List
Unexpected things happen during most projects. Work may be harder than expected, take longer, additional tasks discovered half way through the project, etc. These events should be documented in this work tab, specific action item(s) defined to correct them and the action item should be assigned to someone on the project team to make sure they happen. One issue may drive multiple action items. Until the action items are closed the Project Leader should track them and record their status in the RYGC column. INSTRUCTIONS: STEP 1 - Identify and document issues as you communicate with the team and track against the Deliverables and RACI. STEP 2 - Identify and document action items with ownership and due date to resolve the issue. STEP 3 - Track issue and action items to closure using the RYGC and comments fields.
Ref. No. | Issue | Action Item | Owner | Due Date | R-Y-G-C | Comment
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on F10: R = off plan no recovery plan yet Y = off plan with path to recovery G = on plan C = Complete
TOC

## Close Out Check List
Project Name Will Be Copied from TOC Worksheet
Close Out Check List
Before you close the project confirm that the following have all been completed.
Ref. | Task | Complete?
1 | Have all of the tasks in the RACI been completed, and deliverables met their SMART metrics? |  | TOC
2 | Have all of the issues and action items been resolved or confirmed as no longer needed to complete the project?
3 | Did the sponsor and customers agree that the intention of the project was completed and that the team should close the project?
4 | Have you captured lessons learned and shared them others?
5 | Have you recognized the team somehow?
TOC

## Project Costs
Project Name Will Be Copied from TOC Worksheet
Appendix 1: Project Costs
Program Costs |  |  |  | Total Project Cost: | 93500 | 96520
Ref | Associated Task | Cost Description | Cost Rate | Units | Estimated Cost | Actual Cost | Task List (for reference)
1 | N/A | PjM: 50% for 6 months | 50% x $100K/year | 6 mnths | 25000 | 24000 | N/A
4 | Task 1 | parts | n/a | n/a | 15000 | 14520 | Multiple
3 | Task 2 | fuel | $3/gallon | 500 gallons | 1500 | 2000 | Task 1
2 | Task 4 | test cell occupancy | $5000/day | 10 days | 50000 | 55000 | Task 2
5 | Task 5 | travel | n/a | n/a | 2000 | 1000 | Task 3
6 | [6 empty] | Task 4
7 | [6 empty] | Task 5
8 | [6 empty] | Task 6
9 | [6 empty] | Task 7
10 | [6 empty] | Task 8
11 | [6 empty] | Task 9
12 | [6 empty] | Task 10
13 | [6 empty] | Task 11
14 | [6 empty] | Task 12
15 | [6 empty] | Task 13
16 | [6 empty] | Task 14
17 | [6 empty] | Task 15
18 | [6 empty] | Task 16
19 | [6 empty] | Task 17
20 | [6 empty] | Task 18
21 | [6 empty] | Task 19
22 | [6 empty] | Task 20
23 | [6 empty] | Task 21
24 | [6 empty] | Task 22
25 | [6 empty] | Task 23
26 | [6 empty] | Task 24
27 | [6 empty] | Task 25
28 | [6 empty] | Task 26
29 | [6 empty] | Task 27
30 | [6 empty] | Task 28
Task 29
Task 30
Note on B17: Use pull down arrow to select which task each cost is associated with. Use "N/A" when a cost is not driven by a specific task. Use "multiple" if a cost applies to multiple tasks.
Note on C17: Include a description of the cost. Include supplier and/or vendor if there is one.
Note on D17: For reference only. Include cost rate to help explain the basis of the cost.
Note on E17: For reference only. Include comment explaining the quantity or volume needed.
Note on F17: Include numerical estimate for cost.
Note on G17: When possible, include actual final costs.
Note on J17: Copies task names from RACI schedule for reference.
Note on J18: Some project costs may not be due to a specific task.
Note on J19: Use when a cost applies to multiple tasks
Most projects are justified based on the value they will provide vs. the costs to run them. For small projects, these costs may be estimated before the team is assigned the work without an expectation for the team to manage the costs. Some small projects may need to have the costs associated with running it estimated and tracked. (Most large projects must have their costs tracked.) The sponsor and Management team should be consulted about the need to track costs.
This can be used to estimate project costs by focusing on one task at a time. Costs not associated with a specific task or with multiple tasks should be included.
INSTRUCTIONS:
(before you start, delete the examples shown in the chart below.)
STEP 1 - Identify costs for each task.
STEP 2 - To enter the costs, select a task from the pull down lists in the cells under the "Associated Task" column and then fill in the other columns.
STEP 3 - Consider costs associated with multiple tasks and no specific task. For example, this should include time for project team members . NB: Even if labor costs are not charged to the project, it's a good idea to show the expected work load of the project team. Leave the cost columns blank or just show "NA"
STEP 4 - Use the "sort by task" macro button to sort the data by associated tasks.
STEP 5 - Update the actual costs as the project progresses.
Sort by Task
TOC